## Sheet1
Task/Element | Duration (days) | Zamara | Silva | White | Negri
Setup of Documentation | 1 | X
Setup of Github | 1 |  |  | X
Group Communication methods/ availability | 1 | X |  |  | X
Weather Station Research | 5 | X
Understanding of project between group | 1 | X | X | X | X
Scope justification | 1 |  | X | X | X
Limits and Execlusions | 2 |  | X
User Stories | 4 | X |  | X
User case diagram | 2 |  | X |  | X
User case Description | 1 |  | X |  | X
Class Diagram | 1 |  | X | X | X
Relationship diagram | 1 |  |  | X
Graphical User Interface Design | 3 | X | X | X | X
GUI Testing and adjusting | 2 | X |  |  | X
Project development documentation and finalising documentation | 3 | X | X | X | X
User Log in function | 1 |  | X | X
Develop functions for each of the required sensors to be used | 7 | X | X | X | X
Develop Function for machine Calibration | 5 |  |  | X | X
Develop Automatic upload mode | 7 |  | X |  | X
Tutorial for device | 9 | X
Manufacturer's requirements | 7 |  | X
Functions for protecting data | 4 |  |  |  | X
Data Security | 2 |  |  | X
function to show time and date on the device | 2 |  |  |  | X
Alarms and emergency functions | 3 |  | X
Password resetting function | 1 |  | X
Product testing | 5 | X | X | X | X
Product Refinement | 5 |  | X | X | X
Completion and Submission of Project | 1 | X | X | X | X